## Slide 1
CASPAA
SCHOOL OPERATING SYSTEM
Strategy & Roadmap
CASPAA School Operating System
Built new in eight weeks. What a school runs on first, then the apps.
3 August to 25 September 2026 · Owner: Product · Draft for stakeholder review

## Slide 2
CASPAA
SCHOOL OPERATING SYSTEM
Vision
Where this ends up if the strategy works.
A school runs its whole day on CASPAA and nobody in the building keeps a parallel paper record. That is the test.
The school
Enrolment, the register, results and fees in one place. The bursar stops reconciling by hand. The head sees the collection rate without having to ask for it.
The parent
An icon on the phone that answers both questions: what do I owe, and how is my child doing. Statement, receipt, report card, and a way to reach the teacher.
CASPAA
A vertical operating system rather than a module vendor. Priced per student, so revenue grows with the schools we serve and not only with the number we sign.
Eight weeks gets us the first two steps. A school running a full term on the system, and apps in the hands of the parents, teachers and students who are never at a desk.

## Slide 3
CASPAA
SCHOOL OPERATING SYSTEM
Strategy
Data, insights, beliefs, bets. This slide covers Data and Insights.
Data
What we know
· Schools run the day on paper registers, spreadsheets and WhatsApp. Who has paid and who owes is a question with no fast answer.
· Attendance, results and report cards are computed by hand, and the errors surface a term later in front of parents.
· The incumbent is spreadsheets and WhatsApp, not a rival product. Free, fragmented, no audit trail.
· Connections drop in most of the buildings we sell into. Cloud-only tools stop at the door.
· Tens of thousands of Nigerian private schools are digitising for the first time.
Insights
What we learned
· Schools are not short of records. They are short of the operating loop that produces those records without hand-work. Managing records and running a school are different products.
· Fees is the problem a proprietor will pay to solve this term. Everything else we sell is bought on the back of it.
· Parents and students live on a phone; office staff live at a desk. One product shaped for both surfaces means the phone loses.
· Offline is a condition of the building, not a feature of the software.
Strategy 1 of 2

## Slide 4
CASPAA
SCHOOL OPERATING SYSTEM
Strategy
Data, insights, beliefs, bets. This slide covers Beliefs and Bets.
Beliefs
What we think wins
· The operating week is the product: enrol, timetable, register, marks, invoice, receipt, message the parent. Everything else is an addition to it.
· Whoever runs a school's operating layer earns the payment flow on top of it. That order does not reverse.
· A school onboards once, and judges us on what it finds in that first week. Fewer modules working beats more modules partly built.
· Trust is built on the fee conversation. An itemised statement a parent can read does more for retention than any academic feature.
Bets
What we are backing
· Build new against the specification rather than growing the prototype. The prototype proved the shape of the product; it was never the foundation.
· Four weeks to a product a school can run a term on, then four weeks on the apps for parents, teachers and students.
· One app shell across the three roles, with the interface changing by role.
· Put it into one pilot school at week 4 and let that school's term set the order of Phase 2.
Strategy 2 of 2

## Slide 5
CASPAA
SCHOOL OPERATING SYSTEM
How we chose the order
One question decides Phase 1: can a school get through a full term on it?
1. If a school cannot complete a term without it, it is Phase 1. Enrol, timetable, register, results, report cards, invoices, payments, tell the parents.
2. Daily beats termly, and termly beats annual. The register runs 190 days a year. Report cards run three times. Alumni records, once.
3. Anything that blocks money coming in outranks everything except the spine. Invoices and reconciliation are why the proprietor signed, and how we get paid ourselves.
4. Ship what we can finish. Scope comes out before the date moves. A half-built module in a live school costs more than a missing one.
5. The apps ship on a real API. Phase 1 delivers the API the apps consume, which is what lets app work start on solid ground in week 5.
The line we hold. Phase 1 is finished when a school can complete a term on it. Everything that does not serve that moves to Phase 2, whichever plan it is sold in and however easy it would have been to add.

## Slide 6
CASPAA
SCHOOL OPERATING SYSTEM
Goals
Two gates, four weeks apart. Baseline is today, 29 July 2026.
Gate 1 - 28 August: a school can run on it
· One pilot school completes a full week with no paper fallback
· Register taken in-app by 90% of classes, every day
· A real term billed, collected and reconciled above 98%
· Every parent reached at least once on a live channel
Gate 2 - 25 September: the apps are in hand
· Parent, teacher and student apps live in both stores
· Half the pilot school's parents installed and signed in
· A register marked on a phone, offline, syncing later
· Assessments, payroll and accounting live for the schools that want them
THE YEAR-ONE NUMBERS THESE SERVE
60
schools onboarded
₦1B+
payments processed
85%
fee-collection rate
99.9%
platform uptime

## Slide 7
CASPAA
SCHOOL OPERATING SYSTEM
Roadmap Themes
Phase 1, weeks 1 to 4, is what a school runs on. Phase 2, weeks 5 to 8, is the apps and the next layer.
Foundations Phase 1
Backend & API · Login & RBAC · Tenancy · Offline
One backend, one login, hard separation between schools, and an app that keeps working when the network drops. Invisible to anyone using it, and load-bearing for every theme after it, including the apps.
Hypothesis. Finish the spine inside two weeks and three squads can run in parallel for the remaining six without tripping over each other.
How we validate it. Seven roles sign in to the seed school and each sees only their own data. A teacher marks a register with the laptop in flight mode and it syncs when the network returns.
Actions: Backend & API, Login & RBAC, Tenancy, Offline
The school day Phase 1
Students · Admissions · Timetable · Register · Results
Enrol a child, put them in a class, take the register, enter the marks, approve them, print the report card. This loop is the school's operating week, and it is what Phase 1 exists to deliver.
Hypothesis. Once a teacher can finish a whole teaching day in the app, the paper copy stops being kept. That is when the data becomes good enough to bill and report from.
How we validate it. One class arm runs a full week end to end. Register daily, marks entered and approved, a report card printed on the school's own template with nobody falling back to a notebook.
Actions: Students & admissions, Classes & timetable, Attendance, Results
Roadmap Themes 1 of 4

## Slide 8
CASPAA
SCHOOL OPERATING SYSTEM
Roadmap Themes
Phase 1, weeks 1 to 4, is what a school runs on. Phase 2, weeks 5 to 8, is the apps and the next layer.
Fees and payments Phase 1
Fee structure · Invoices · Ledger · Payments · Reconciliation
The reason a proprietor signs the contract. Bill a term, show every parent an itemised statement, take the money online, and have it reconcile itself. Our own subscription billing lands here too, priced per student per term off the live roll.
Hypothesis. Parents pay sooner when they can see exactly what they owe and a receipt arrives the moment the money does. Schools renew when the collection rate visibly moves.
How we validate it. The pilot school bills a real term on CASPAA. Payments match automatically above 98%, statements and receipts print correctly, and the owing list agrees with the bank without a spreadsheet.
Actions: Fees & ledger, Payments, Reconciliation, CASPAA billing
Reaching parents Phase 1
Parent portal · Announcements · Consent · WhatsApp & email
A school that cannot reach its parents has bought a filing cabinet. The web portal and the messaging channels come first; the phone app in Phase 2 sits on top of the same work.
Hypothesis. Parents who receive absence alerts and receipts on WhatsApp open the portal without being chased, which is what makes fee reminders work later on.
How we validate it. Every parent at the pilot school receives at least one live message in week 4, and consent for one real school trip is collected entirely in the app.
Actions: Parent portal, Announcements & consent, WhatsApp & email
Roadmap Themes 2 of 4

## Slide 9
CASPAA
SCHOOL OPERATING SYSTEM
Roadmap Themes
Phase 1, weeks 1 to 4, is what a school runs on. Phase 2, weeks 5 to 8, is the apps and the next layer.
The apps Phase 2
Parent · Teacher · Student · Store release
Phones for the three roles that are not sitting at a desk. Parents, teachers and students. Admin, finance and the operations portal stay on the web, where the work is genuinely desk work.
Hypothesis. Parents will not keep a browser tab for the school, but they will keep an icon. The same is true of students. For teachers it is about marking the register where the class actually is.
How we validate it. Installs on real devices at the pilot school. A teacher marks a register on a phone in a classroom with no signal and it syncs later. A parent pays fees from the app without opening a browser.
Actions: App shell & sync, Parent app, Teacher app, Student app & release
Teaching and learning Phase 2
Assessments · CBT · Lesson plans · Behaviour · Alumni
What a school reaches for once the operating week is running smoothly. Frequently requested, and well placed to follow the essentials rather than compete with them.
Hypothesis. Assessments are what pull students into the product daily rather than at report-card time.
How we validate it. One CBT sitting runs for a real class with real marks, and the results land in the same broadsheet as everything else.
Actions: Assignments & CBT, Lessons & materials, Behaviour & alumni
Roadmap Themes 3 of 4

## Slide 10
CASPAA
SCHOOL OPERATING SYSTEM
Roadmap Themes
Phase 1, weeks 1 to 4, is what a school runs on. Phase 2, weeks 5 to 8, is the apps and the next layer.
Staff, money and scale Phase 2
Payroll & HR · Accounting · Transport · Inventory · Groups
Back office and growth. Payroll and the accounting package are what stop a school keeping a second set of books. Multi-branch closes the plan, sized for the group owners who arrive once the single campus is proven.
Hypothesis. Payroll is the strongest reason an existing school expands its usage rather than churning. Multi-branch raises the price but rarely wins the first deal.
How we validate it. One payroll cycle runs end to end at the pilot school, and its accountant accepts the trial balance without re-keying it. A group owner runs two campuses from one login.
Actions: Payroll & HR, Accounting, Transport, Operations, Multi-branch
Roadmap Themes 4 of 4

## Slide 11
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
Foundations
Backend & API · Login & RBAC · Tenancy · Offline
Action | Why it matters | Milestones (epics) | ETA
Production backend and API | A school's data belongs on a server the apps and the web can both read. | · Data model and schema built from the PRD · REST API with a validation layer, designed for the phone apps to reuse · A pilot school's records loaded and dogfooded internally | Week 1 by 7 Aug
Unified login and RBAC | Seven roles, one front door. Get it wrong and every screen inherits the mistake. | · Role-aware routing from a single login · Permissions enforced server-side, not in the interface · Token-based sessions the apps can use later | Week 1 by 7 Aug
Tenant isolation | Complete separation between schools is the assurance every proprietor asks for first. | · School scoping enforced on every read and write · Automated isolation tests in the build | Weeks 1-2 by 14 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
Foundations 1 of 2

## Slide 12
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
Foundations
Backend & API · Login & RBAC · Tenancy · Offline
Action | Why it matters | Milestones (epics) | ETA
Offline-first behaviour | Registers get marked in classrooms with no signal, so the app has to work without one. | · Installable app, offline reads · Register and results queue, then sync on reconnect | Week 2 by 14 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
Foundations 2 of 2

## Slide 13
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
The school day
Students · Admissions · Timetable · Register · Results
Action | Why it matters | Milestones (epics) | ETA
Students and admissions | Every other module reads the student record, so it is the first thing built. | · Enrolment, bulk CSV import, online applications · Promotion between classes and sessions | Weeks 1-2 by 14 Aug
Sessions, classes and timetable | Terms and class arms are what the register, the results and the fees all hang off. | · Sessions, terms and class arms · Timetable with clash detection · Subject and teacher assignment | Week 2 by 14 Aug
Attendance register | Marked 190 days a year, which makes it the most-used screen in the product. | · Daily class register that works offline · Clock-in and clock-out student register · Automatic parent alert on an unexplained absence | Weeks 2-3 by 21 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
The school day 1 of 2

## Slide 14
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
The school day
Students · Admissions · Timetable · Register · Results
Action | Why it matters | Milestones (epics) | ETA
Results and report cards | Termly, but it is the document a school is judged on by every parent at once. | · Teacher entry, admin approval gate, broadsheet · Printable report cards carrying the school's branding | Weeks 3-4 by 28 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
The school day 2 of 2

## Slide 15
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
Fees and payments
Fee structure · Invoices · Ledger · Payments · Reconciliation
Action | Why it matters | Milestones (epics) | ETA
Fee structure, invoices and the student ledger | The itemised statement of account is the one feature parents ask for by name. | · Fee structure and invoice generation per term · Itemised statement with the discount breakdown · Owing and part-paid filters, advance credit | Weeks 2-3 by 21 Aug
Online payments and receipts | Card, transfer and USSD with an instant receipt is what turns billed into collected. | · Paystack card, bank transfer and USSD · Webhooks and real-time receipts | Weeks 3-4 by 28 Aug
Reconciliation and financial reports | Owners decide on billed against collected. Bursars judge us on the match rate. | · Automatic bank reconciliation above 98% · Billed, collected and outstanding by class and term | Week 4 by 28 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
Fees and payments 1 of 2

## Slide 16
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
Fees and payments
Fee structure · Invoices · Ledger · Payments · Reconciliation
Action | Why it matters | Milestones (epics) | ETA
Our own subscription billing | We charge per student per term, so the invoice has to come off the live roll rather than a fixed figure. | · One pricing source shared by the website and the app · Term invoice computed from live headcount, setup fee as a one-off line | Week 4 by 28 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
Fees and payments 2 of 2

## Slide 17
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 1
Reaching parents
Parent portal · Announcements · Consent · WhatsApp & email
Action | Why it matters | Milestones (epics) | ETA
Parent portal and child dashboards | One login covering several children is the difference between a parent using it and not. | · Per-child view of fees, results and attendance · Statement and receipt download | Week 3 by 21 Aug
Announcements, calendar and digital consent | Consent slips are the paper the front office loses most often. | · Announcements and notice board · School calendar and events · Digital consent with a live response list | Weeks 3-4 by 28 Aug
WhatsApp and email delivery | In-app notifications alone do not reach Nigerian parents. WhatsApp does. | · Provider integration and delivery receipts · Absence, fee and receipt templates | Week 4 by 28 Aug
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.

## Slide 18
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 2
The apps
Parent · Teacher · Student · Store release
Action | Why it matters | Milestones (epics) | ETA
App shell, auth and sync | One shell serving three roles keeps the apps consistent and the release predictable. | · Shared shell with role-aware navigation · Token auth against the Phase 1 API · Offline store and background sync | Weeks 5-6 by 11 Sep
Parent app | The highest-volume audience, and the one that pays. | · Fees, statement and in-app payment · Results, attendance and absence alerts · Consent and announcements with push | Weeks 6-7 by 18 Sep
Teacher app | The register belongs in a pocket, not on a desktop in the staff room. | · Register marking, offline first · Results entry and the diary | Weeks 6-7 by 18 Sep
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
The apps 1 of 2

## Slide 19
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 2
The apps
Parent · Teacher · Student · Store release
Action | Why it matters | Milestones (epics) | ETA
Student app and store release | The app counts once a parent can install it from the store they already use. | · Timetable, assignments, results · Play Store and App Store submission, with the review time budgeted | Weeks 7-8 by 25 Sep
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
The apps 2 of 2

## Slide 20
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 2
Teaching and learning
Assessments · CBT · Lesson plans · Behaviour · Alumni
Action | Why it matters | Milestones (epics) | ETA
Assignments and CBT | Homework and online tests are the reason a student opens the app between terms. | · Assignments with inline marking and resubmission · CBT engine and formative tests | Weeks 5-6 by 11 Sep
Lesson plans and materials | Heads of department want visibility of what is being taught, not just what was marked. | · Lesson plans against the scheme of work · Notes and materials for the student learning area | Weeks 6-7 by 18 Sep
Behaviour, discipline and alumni | Completes the student record: conduct alongside marks, and what happens after they leave. | · Incidents, merits and sanctions · Alumni register and leaving certificates | Week 7 by 18 Sep
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.

## Slide 21
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 2
Staff, money and scale
Payroll & HR · Accounting · Transport · Inventory · Groups
Action | Why it matters | Milestones (epics) | ETA
Payroll, HR and salary advance | The clearest reason a school widens what it uses instead of drifting away. | · Payroll run and payslip distribution · Leave, appraisals, substitute cover · Salary advance against payroll | Weeks 5-6 by 11 Sep
Accounting package | P&L, trial balance and balance sheet are what stop the second set of books. | · Chart of accounts and posting rules · P&L, trial balance, balance sheet · An export the external accountant will accept | Weeks 6-7 by 18 Sep
Transport and authorised pickup | Safety carries more weight with parents than anything on the academic side. | · Routes, assignments, live bus status · Authorised pickup approval | Weeks 6-7 by 18 Sep
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
Staff, money and scale 1 of 2

## Slide 22
CASPAA
SCHOOL OPERATING SYSTEM
THEME DETAILS · PHASE 2
Staff, money and scale
Payroll & HR · Accounting · Transport · Inventory · Groups
Action | Why it matters | Milestones (epics) | ETA
Inventory, house points and surveys | What the bursar and the sports master ask for by the second term. | · Inventory with low-stock alerts · House points, leaderboards, inter-house competitions · Surveys and feedback forms | Weeks 7-8 by 25 Sep
Multi-branch groups | One login across campuses, and the feature a group owner signs for. | · Group overview and branch switcher · Add-branch on-ramp · Consolidated finance and enrolment roll-up | Week 8 by 25 Sep
Done means tenant-scoped, role-correct, all states handled, responsive, audited, offline-tolerant, acceptance criteria signed off.
Staff, money and scale 2 of 2

## Slide 23
CASPAA
SCHOOL OPERATING SYSTEM
The eight weeks at a glance
PHASE 1 · A SCHOOL CAN RUN ON IT
PHASE 2 · THE APPS, AND WHAT COMES NEXT
3 Aug - 25 Sep 2026
Wk 1
3 Aug
Wk 2
10 Aug
Wk 3
17 Aug
Wk 4
24 Aug
Wk 5
31 Aug
Wk 6
7 Sep
Wk 7
14 Sep
Wk 8
21 Sep
Foundations
4 actions · weeks 1-2
The school day
4 actions · weeks 1-4
Fees and payments
4 actions · weeks 2-4
Reaching parents
3 actions · weeks 3-4
The apps
4 actions · weeks 5-8
Teaching and learning
3 actions · weeks 5-7
Staff, money and scale
5 actions · weeks 5-8
Week 4 is a gate. Phase 2 opens once a real school has run a real week on Phase 1, so the app work starts against a product that is already holding up in a classroom.
Roadmap overview

## Slide 24
CASPAA
SCHOOL OPERATING SYSTEM
Eight-week roadmap
PHASE 1 · A SCHOOL CAN RUN ON IT
PHASE 2 · THE APPS, AND WHAT COMES NEXT
3 Aug - 25 Sep 2026
Wk 1
3 Aug
Wk 2
10 Aug
Wk 3
17 Aug
Wk 4
24 Aug
Wk 5
31 Aug
Wk 6
7 Sep
Wk 7
14 Sep
Wk 8
21 Sep
FOUNDATIONS
Backend & API
Login & RBAC
Tenancy
Tenant isolation
Offline
Offline
THE SCHOOL DAY
Students & admissions
Students & admissions
Classes & timetable
Attendance
Attendance register
Results
Results & report cards
Each bar is the working window for one action. Names sit on the left.
Roadmap detail 1 of 4

## Slide 25
CASPAA
SCHOOL OPERATING SYSTEM
Eight-week roadmap
PHASE 1 · A SCHOOL CAN RUN ON IT
PHASE 2 · THE APPS, AND WHAT COMES NEXT
3 Aug - 25 Sep 2026
Wk 1
3 Aug
Wk 2
10 Aug
Wk 3
17 Aug
Wk 4
24 Aug
Wk 5
31 Aug
Wk 6
7 Sep
Wk 7
14 Sep
Wk 8
21 Sep
FEES AND PAYMENTS
Fees & ledger
Fees, invoices & ledger
Payments
Payments & receipts
Reconciliation
CASPAA billing
REACHING PARENTS
Parent portal
Announcements & consent
Announcements & consent
WhatsApp & email
Each bar is the working window for one action. Names sit on the left.
Roadmap detail 2 of 4

## Slide 26
CASPAA
SCHOOL OPERATING SYSTEM
Eight-week roadmap
PHASE 1 · A SCHOOL CAN RUN ON IT
PHASE 2 · THE APPS, AND WHAT COMES NEXT
3 Aug - 25 Sep 2026
Wk 1
3 Aug
Wk 2
10 Aug
Wk 3
17 Aug
Wk 4
24 Aug
Wk 5
31 Aug
Wk 6
7 Sep
Wk 7
14 Sep
Wk 8
21 Sep
THE APPS
App shell & sync
Shell, auth & sync
Parent app
Parent app
Teacher app
Teacher app
Student app & release
Student app & release
TEACHING AND LEARNING
Assignments & CBT
Assignments & CBT
Lessons & materials
Lesson plans & materials
Behaviour & alumni
Each bar is the working window for one action. Names sit on the left.
Roadmap detail 3 of 4

## Slide 27
CASPAA
SCHOOL OPERATING SYSTEM
Eight-week roadmap
PHASE 1 · A SCHOOL CAN RUN ON IT
PHASE 2 · THE APPS, AND WHAT COMES NEXT
3 Aug - 25 Sep 2026
Wk 1
3 Aug
Wk 2
10 Aug
Wk 3
17 Aug
Wk 4
24 Aug
Wk 5
31 Aug
Wk 6
7 Sep
Wk 7
14 Sep
Wk 8
21 Sep
STAFF, MONEY AND SCALE
Payroll & HR
Payroll, HR & advances
Accounting
Accounting package
Transport
Transport & pickup
Operations
Operations
Multi-branch
Each bar is the working window for one action. Names sit on the left.
Roadmap detail 4 of 4

## Slide 28
CASPAA
SCHOOL OPERATING SYSTEM
What we are not building
Worth stating plainly, because each of these has been asked for at least once.
Held by decision
· Fee lending: applications, credit scoring, approval, disbursement, repayment
· It ships gated off and stays documented so it can resume without a rewrite
Not in these eight weeks
· An admin or finance app. That work is desk work and stays on the web
· AI report comments and academic insights
· Advanced analytics and scheduled reports for the operations portal
Later, if the data supports it
· Bulk disbursement and NIBSS direct settlement
· Savings and investment products, which need a licence we do not hold
· AI underwriting, which needs a far larger dataset than we will have this year
Phase 2 is reviewed at the week-4 gate. Its order is set against what the first live schools are reaching for, which we will know by then and do not know now.

## Slide 29
CASPAA
SCHOOL OPERATING SYSTEM
What has to hold, and what would move the date
ASSUMPTIONS
RISKS
Three squads from week 3
The school day, fees and parent-facing work have no hard dependency on each other once the spine is done.
One app shell across the three roles
Parent, teacher and student share a shell and differ by role, which is what keeps the app work inside four weeks.
The prototype is the reference, not the foundation
PRD v4 and the working prototype specify the behaviour. These eight weeks build the product new against them, starting from schema and API in week 1.
Week 2 slips
The spine is unfinished, nothing else starts cleanly and the apps lose their API. Weeks 1 and 2 carry no other scope so the team can absorb an overrun.
Store review eats week 8
Play and App Store review is outside our control and can take days. Submission is planned for week 7, not week 8.
Done gets traded for speed
Half-finished work in a live school costs more than a missing feature, so done is enforced at the merge.
Decision needed before week 5: package the existing offline web app for the stores, or build the apps native. Packaging is what fits the four weeks in this plan. Native is a larger piece of work and needs its own schedule.